## Pdp_3feb23
MELODY & MOMON - 3D Animated Series 52X7' (26+26) - updated May 14th 2024 | [48 empty] | 26 script (30 nov) | 26 script (30 nov) | [33 empty] | ferie ? |  | 26 master broadcaster 31-ago | [12 empty] | 27-52 master broadcaster 30-nov
TOTAL PROD_WEEKS | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16 | WEEK 17 | WEEK 18 | WEEK 19 | WEEK 20 | WEEK 21 | WEEK 22 | WEEK 23 | WEEK 24 | WEEK 25 | WEEK 26 | WEEK 27 | WEEK 28 | WEEK 29 | WEEK 30 | WEEK 31 | WEEK 32 | WEEK 33 | WEEK 34 | WEEK 35 | WEEK 36 | WEEK 37 | WEEK 38 | WEEK 39 | WEEK 40 | WEEK 41 | WEEK 42 | WEEK 43 | WEEK 44 | WEEK 45 | WEEK 46 | WEEK 47 | WEEK 48 | WEEK 49 | WEEK 50 | WEEK 51 | WEEK 52 | WEEK 53 | WEEK 54 | WEEK 55 | WEEK 56 | WEEK 57 | WEEK 58 | WEEK 59 | WEEK 60 | WEEK 61 | WEEK 62 | WEEK 63 | WEEK 64 | WEEK 65 | WEEK 66 | WEEK 67 | WEEK 68 | WEEK 69 | WEEK 70 | WEEK 71 | WEEK 72 | WEEK 73 | WEEK 74 | WEEK 75 | WEEK 76 | WEEK 77 | WEEK 78 | WEEK 79 | WEEK 80 | WEEK 81 | WEEK 82 | WEEK 83 |  | WEEK 84 | WEEK 85 | WEEK 86 | WEEK 87 | WEEK 88 | WEEK 89 | WEEK 90 | WEEK 91 | WEEK 92 | WEEK 93 | WEEK 94 | WEEK 95 | WEEK 96 | WEEK 97 | WEEK 98
Dubbing ENG | bar: WEEK 17; WEEK 21; WEEK 25; WEEK 28; WEEK 30; WEEK 33
Dubbing IT | [60 empty] | EPS 01-13 DUBBING ITA (no PU) | [6 empty] | EPS 14-26 DUBBING ITA (no PU) | [6 empty] | EPS 27-39 DUBBING ITA (no PU) | [6 empty] | EPS 40-52 DUBBING ITA (no PU)
EPISODI
1 | WEEK 2: polish; WEEK 6: polish; WEEK 7: BDL AS; WEEK 8: 2D model; WEEK 9: 2D model; WEEK 10: 2D model; WEEK 11: 2D model; WEEK 12: DELIVERY CH/PR; WEEK 13: Modeling; WEEK 18: Texture; WEEK 22: 10; WEEK 23: Delivery anim 3D; WEEK 24: RIG; WEEK 29: 6; WEEK 30: Layout/Anim/Lighting |  |  |  |  | 11 | 12 | Render |  | Compositing |  | Broadcast |  | REV | CHECK | DELIVERY SOURCE | [10 empty] | DUB ITA | [7 empty] | MIX ENG | RTKs APP | MIX ENG | Master ENG | [13 empty] | 26 master broadcaster 31-ago
| WEEK 2: Bible review & 1script; WEEK 7: locked; WEEK 8: REV; WEEK 9: Broadcast; WEEK 10: Broadcast; WEEK 11: Broadcast; WEEK 12: Broadcast; WEEK 13: Broadcast; WEEK 14: Story RTK; WEEK 15: Story RTK; WEEK 16: Story RTK; WEEK 17: VB CONFO locked | [27 empty] | DUB ENG | [5 empty] | MASTER IT | AD/SUB no broadcaster | AD/SUB no broadcaster | AD/SUB no broadcaster | AD/SUB no broadcaster | AD/SUB no broadcaster | [11 empty] | 26 master broadcaster 31-ago
| WEEK 7: ENG VOICES; WEEK 12: Delivery pre-3D; WEEK 13: CAM 3D | [8 empty] | Hypotesis 2 musicians |  | music | music | SD | note | [15 empty] | MIX ITA | Broadcast | MIX ITA | [18 empty] | 26 master broadcaster 31-ago
2 | WEEK 9: polish; WEEK 10: BDL; WEEK 11: 2D model; WEEK 12: 2D model; WEEK 13: 2D model; WEEK 14: 2D model; WEEK 15: DELIVERY CH/PR; WEEK 17: Modeling; WEEK 22: Texture; WEEK 28: 12; WEEK 29: Delivery anim 3D; WEEK 30: RIG; WEEK 32: 3; WEEK 33: Layout/Anim/Lighting | [8 empty] | 12 | Render |  | Compositing |  | Broadcast | REV | CHECK | DELIVERY SOURCE | [8 empty] | DUB ITA | [7 empty] | MIX ENG | RTKs APP | MIX ENG | Master ENG | [13 empty] | 26 master broadcaster 31-ago
| WEEK 4: broadcaster; WEEK 5: polish; WEEK 8: rev. + torna a broadcaster; WEEK 9: broadcaster; WEEK 13: CAM 3D; WEEK 16: Delivery pre-3D; WEEK 17: ENG VOICES | [27 empty] | DUB ENG | [5 empty] | MASTER IT | AD/SUB no broadcaster | AD/SUB no broadcaster | AD/SUB no broadcaster | AD/SUB no broadcaster | AD/SUB no broadcaster | [11 empty] | 26 master broadcaster 31-ago
| WEEK 5: DIR/3D notes; WEEK 6: polish; WEEK 8: Max /Marcello cam e cu; WEEK 9: Story thumb; WEEK 17: Broadcast prev. a broadcaster; WEEK 18: Story RTK + cam; WEEK 19: Story RTK + cam; WEEK 20: Broadcast; WEEK 21: Story RTK; WEEK 22: VB CONFO locked; WEEK 23: VB CONFO locked; WEEK 24: 2D AS model COL; WEEK 25: note; WEEK 26: Modeling AS; WEEK 27: Texture AS | [13 empty] | music | music | SD | note | [12 empty] | MIX ITA | Broadcast | MIX ITA
3 | [60 empty] | DUB ITA | [24 empty] | 26 master broadcaster 31-ago
[9 empty] | Pre-BDL | thumb | BDL | 2D model | 2D model | 2D model | 2D model | DELIVERY CH/PR | ENG VOICES | Delivery SB | SB BRIEF | thumb ?? | Story RG |  |  | directing - RTK | Story CU+timing | Broadcast | Story RTK | Story RTK | VB CONFO locked | VB CONFO locked |  | Delivery anim 3D | RIG |  |  | Layout/Anim/Lighting | [10 empty] | 12 | Render |  | Compositing | Broadcast | REV | CHECK | DELIVERY SOURCE | [8 empty] | DUB ENG | [5 empty] | MIX ENG | RTKs APP | MIX ENG | Master ENG | [13 empty] | 26 master broadcaster 31-ago
| WEEK 1: draft + note; WEEK 2: outline; WEEK 3: note+ v2; WEEK 4: outline+script v1 + note; WEEK 6: script v2 + note (+ v3); WEEK 8: broadcaster; WEEK 10: POLISH ENG; WEEK 18: CAM 3D; WEEK 21: Delivery pre-3D; WEEK 22: Modeling; WEEK 27: Texture; WEEK 31: 10 | [29 empty] | MIX ITA | Broadcast | MIX ITA |  | MASTER IT | AD/SUB no broadcaster | AD/SUB no broadcaster | AD/SUB no broadcaster | AD/SUB no broadcaster | AD/SUB no broadcaster | [11 empty] | 26 master broadcaster 31-ago
| WEEK 9: polish; WEEK 27: BDL AS; WEEK 28: 2D AS model COL; WEEK 29: note; WEEK 30: Modeling AS; WEEK 31: Texture AS | [16 empty] | music | music | SD | note | [30 empty] | 26 master broadcaster 31-ago
4 | WEEK 17: ENG VOICES | [25 empty] | DUB ITA | [24 empty] | 26 master broadcaster 31-ago
[12 empty] | Pre-BDL | thumb | BDL | 2D model | 2D model | 2D model | 2D model | DELIVERY CH/PR | Delivery SB | CAM 3D | SB BRIEF | thumb ?? | Story RG |  |  | directing - RTK | Story CU+timing | Broadcast | Story RTK | VB CONFO locked | VB CONFO locked | Delivery anim 3D | RIG |  |  | Layout/Anim/Lighting | [9 empty] | 11 | Render |  | Compositing | Broadcast | REV | CHECK | DELIVERY SOURCE | [8 empty] | DUB ENG | [5 empty] | MIX ENG | RTKs APP | MIX ENG | Master ENG | [13 empty] | 26 master broadcaster 31-ago
| WEEK 5: outline + note; WEEK 6: v2 + note PROD; WEEK 7: V3 + note broadcaster; WEEK 8: script v1 + note; WEEK 10: script v2 + note+ v3; WEEK 12: broadcaster; WEEK 13: POLISH ENG; WEEK 22: Delivery pre-3D; WEEK 23: Modeling; WEEK 28: Texture; WEEK 32: 10 | [29 empty] | MIX ITA | Broadcast | MIX ITA |  | MASTER IT | AD/SUB no broadcaster | AD/SUB no broadcaster | AD/SUB no broadcaster | AD/SUB no broadcaster | AD/SUB no broadcaster | [11 empty] | 26 master broadcaster 31-ago
| WEEK 28: BDL AS; WEEK 29: 2D AS model COL; WEEK 30: note; WEEK 31: Modeling AS; WEEK 32: Texture AS | [17 empty] | music | music | SD | note | [29 empty] | 26 master broadcaster 31-ago
26 master broadcaster 31-ago
5 | [60 empty] | DUB ITA | [24 empty] | 26 master broadcaster 31-ago
| WEEK 13: Pre-BDL; WEEK 14: thumb; WEEK 15: BDL; WEEK 16: 2D model; WEEK 17: 2D model; WEEK 18: 2D model; WEEK 19: 2D model; WEEK 20: DELIVERY CH/PR; WEEK 23: Delivery pre-3D; WEEK 24: Modeling; WEEK 29: Texture; WEEK 33: 10; WEEK 34: Delivery anim 3D; WEEK 35: RIG |  |  | Layout/Anim/Lighting | [9 empty] | 11 | Render |  | Compositing | Broadcast | REV | CHECK | DELIVERY SOURCE | [7 empty] | DUB ENG | [5 empty] | MIX ENG | RTKs APP | MIX ENG | Master ENG | [13 empty] | 26 master broadcaster 31-ago
| WEEK 6: outline + note; WEEK 7: v2 + note PROD; WEEK 8: V3 + note broadcaster; WEEK 9: script v1 + note; WEEK 11: script v2 + note+ v3; WEEK 13: broadcaster; WEEK 14: POLISH ENG; WEEK 17: ENG VOICES; WEEK 21: Delivery SB; WEEK 22: CAM 3D; WEEK 23: SB BRIEF; WEEK 24: thumb ??; WEEK 25: Story RG; WEEK 28: directing - RTK; WEEK 29: Story CU+timing; WEEK 30: Broadcast; WEEK 31: Story RTK; WEEK 32: Story RTK; WEEK 33: VB CONFO locked | [29 empty] | MIX ITA | Broadcast | MIX ITA |  | MASTER IT | AD/SUB no broadcaster | AD/SUB no broadcaster | AD/SUB no broadcaster | AD/SUB no broadcaster | AD/SUB no broadcaster | [11 empty] | 26 master broadcaster 31-ago
| WEEK 29: BDL AS; WEEK 30: 2D AS model COL; WEEK 31: note; WEEK 32: Modeling AS; WEEK 33: Texture AS | [18 empty] | music | music | SD | note | [28 empty] | 26 master broadcaster 31-ago
26 master broadcaster 31-ago
12
8