## Sheet1
Mobo
|  |  | giorni lav | start | end | pre | WD | g tot
Boo |  |  | 355.5 | 2024-09-02 | 2026-01-28 |  | 2026-01-12 | 513 |  |  |  | libero
Modeling & Texturing |  |  | 132 | 2024-09-02 | 2025-03-13 |  | 2025-03-05 | 192
Main content | 2 | 12 | 12 | 2024-09-02 | 2024-09-17 |  | 2024-09-18 | 15 | 2024-06-10 | 2024-06-17 | 45461 | 2024-06-18 | 7
Main character | 1 |  | 12 | 2024-09-02 | 2024-09-17 |  | 2024-09-18 | 15
Main character | 1 |  | 12 | 2024-09-02 | 2024-09-17 |  | 2024-09-18 | 15
Main content | 19 | 12 | 120 | 2024-09-18 | 2025-03-13 | 3 | 2025-03-05 | 176
Secondary character | 10 |  | 120 | 2024-09-18 | 2025-03-13 |  | 2025-03-05 | 176
Secondary character | 9 |  | 108 | 2024-09-18 | 2025-02-25 |  | 2025-02-17 | 160
Main content | 4 | 30 | 30 | 2024-09-02 | 2024-10-11 |  | 2024-10-14 | 39
Main macro environment (+Look Dev) | 1 |  | 30 | 2024-09-02 | 2024-10-11 |  | 2024-10-14 | 39
Main macro environment (+Look Dev) | 1 |  | 30 | 2024-09-02 | 2024-10-11 |  | 2024-10-14 | 39
Main macro environment (+Look Dev) | 1 |  | 30 | 2024-09-02 | 2024-10-11 |  | 2024-10-14 | 39
Main macro environment (+Look Dev) | 1 |  | 30 | 2024-09-02 | 2024-10-11 |  | 2024-10-14 | 39
Main content | 10 | 5 | 15 | 2024-10-14 | 2024-11-04 | 9 | 2024-11-04 | 21
Incidental not speaking characters | 3 |  | 15 | 2024-10-14 | 2024-11-04 |  | 2024-11-04 | 21
Incidental not speaking characters | 3 |  | 15 | 2024-10-14 | 2024-11-04 |  | 2024-11-04 | 21
Incidental not speaking characters | 2 |  | 10 | 2024-10-14 | 2024-10-25 |  | 2024-10-28 | 11
Incidental not speaking characters | 2 |  | 10 | 2024-10-14 | 2024-10-25 |  | 2024-10-28 | 11
Modeling & Texturing |  |  | 261.5 | 2024-10-28 | 2025-11-13 |  | 2025-10-28 | 381
Episodic content | 8 | 12 | 60 | 2025-02-26 | 2025-05-23 |  | 2025-05-21 | 86
Comparse umane (2 adulti+bambino) | 3 |  | 36 | 2025-03-14 | 2025-05-07 | 7 | 2025-05-05 | 54
Comparse umane (2 adulti+bambino) | 5 |  | 60 | 2025-02-26 | 2025-05-23 | 8 | 2025-05-21 | 86
Episodic content | 30 | 0.5 | 13.5 | 2025-05-08 | 2025-05-27 |  | 2025-05-27 | 19
Episodic character (cambio colore vestito o cappelli) | 27 |  | 13.5 | 2025-05-08 | 2025-05-27 | 21 | 2025-05-27 | 19
Episodic character (cambio colore vestito o cappelli) | 3 |  | 1.5 | 2025-05-26 | 2025-05-27 | 22 | 2025-05-27 | 1
Episodic content | 8 | 12 | 48 | 2025-05-27 | 2025-08-04 |  | 2025-08-01 | 69
Episodic speaking human characters | 4 |  | 48 | 2025-05-27 | 2025-08-04 | 24 | 2025-08-01 | 69
Episodic speaking human characters | 4 |  | 48 | 2025-05-27 | 2025-08-04 | 25 | 2025-08-01 | 69
Episodic content | 12 | 12 | 72 | 2025-08-04 | 2025-11-13 |  | 2025-11-12 | 101
Episodic incidental characters | 6 |  | 72 | 2025-08-04 | 2025-11-13 | 27 | 2025-11-12 | 101
Episodic incidental characters | 6 |  | 72 | 2025-08-04 | 2025-11-13 | 28 | 2025-11-12 | 101
Episodic content | 358 | 1.5 | 184 | 2024-10-28 | 2025-07-25 |  | 2025-07-11 | 270
Episodic Props | 119 |  | 179 | 2024-11-05 | 2025-07-25 | 15 | 2025-07-14 | 262
Episodic Props | 119 |  | 179 | 2024-11-05 | 2025-07-25 | 16 | 2025-07-14 | 262
Episodic Props | 119 |  | 179 | 2024-10-28 | 2025-07-18 | 17 | 2025-07-04 | 263
Episodic content | 58 | 0.5 | 29 | 2025-07-02 | 2025-08-11 |  | 2025-08-12 | 40
Episodic Prop (solo TX) |  |  | 29 | 2025-07-02 | 2025-08-11 | 100 | 2025-08-12 | 40
Episodic content | 10 | 20 | 204 | 2024-10-28 | 2025-08-25 |  | 2025-08-08 | 301
Episodic environment | 1 |  | 20 | 2025-07-28 | 2025-08-25 | 33 | 2025-08-25 | 28
Episodic environment | 1 |  | 20 | 2025-07-28 | 2025-08-25 | 34 | 2025-08-25 | 28
Episodic environment | 1 |  | 20 | 2025-07-21 | 2025-08-18 | 35 | 2025-08-18 | 28
Episodic environment | 7 |  | 140 | 2024-10-28 | 2025-05-23 | 18 | 2025-05-12 | 207
Episodic content | 2 | 5 | 69 | 2025-05-26 | 2025-09-01 |  | 2025-08-29 | 98
Night version - EXT Macro environment | 1 |  | 5 | 2025-08-26 | 2025-09-01 | 40 | 2025-09-02 | 6
Night version - EXT Macro environment | 1 |  | 5 | 2025-05-26 | 2025-05-30 | 42 | 2025-06-02 | 4
Episodic content | 2 | 10 | 69 | 2025-06-03 | 2025-09-08 |  | 2025-09-08 | 97
Seasonal version - EXT Macro environment | 1 |  | 10 | 2025-08-26 | 2025-09-08 | 39 | 2025-09-09 | 13
Seasonal version - EXT Macro environment | 1 |  | 10 | 2025-06-03 | 2025-06-16 | 45 | 2025-06-17 | 13
Formulas:
WD = WORKDAY([start],[giorni lav])

## Sheet2
Mobo
|  |  |  | start | end |  |  | WD
Boo |  |  | 355.5 | 2024-09-02 | 2026-01-28 |  | 503.97 | 2026-01-12 | 513
Modeling & Texturing |  |  | 132 | 2024-09-02 | 2025-03-13 |  | 503.97 | 2025-03-05 | 192
Main content | 2 | 12 | 12 | 2024-09-02 | 2024-09-17 |  | 503.97 | 2024-09-18 | 15
Main character | 1 |  | 12 | 2024-09-02 | 2024-09-17 |  | 503.97 | 2024-09-18 | 15
Main character | 1 |  | 12 | 2024-09-02 | 2024-09-17 |  | 0 | 2024-09-18 | 15
Main content | 19 | 12 | 120 | 2024-09-18 | 2025-03-13 | 3 | 0 | 2025-03-05 | 176
Secondary character | 10 |  | 120 | 2024-09-18 | 2025-03-13 |  | 0 | 2025-03-05 | 176
Secondary character | 9 |  | 108 | 2024-09-18 | 2025-02-25 |  | 0 | 2025-02-17 | 160
Main content | 4 | 30 | 30 | 2024-09-02 | 2024-10-11 |  | 0 | 2024-10-14 | 39
Main macro environment (+Look Dev) | 1 |  | 30 | 2024-09-02 | 2024-10-11 |  | 0 | 2024-10-14 | 39
Main macro environment (+Look Dev) | 1 |  | 30 | 2024-09-02 | 2024-10-11 |  | 0 | 2024-10-14 | 39
Main macro environment (+Look Dev) | 1 |  | 30 | 2024-09-02 | 2024-10-11 |  | 0 | 2024-10-14 | 39
Main macro environment (+Look Dev) | 1 |  | 30 | 2024-09-02 | 2024-10-11 |  | 0 | 2024-10-14 | 39
Main content | 10 | 5 | 15 | 2024-10-14 | 2024-11-04 | 9 | 0 | 2024-11-04 | 21
Incidental not speaking characters | 3 |  | 15 | 2024-10-14 | 2024-11-04 |  | 0 | 2024-11-04 | 21
Incidental not speaking characters | 3 |  | 15 | 2024-10-14 | 2024-11-04 |  | 0 | 2024-11-04 | 21
Incidental not speaking characters | 2 |  | 10 | 2024-10-14 | 2024-10-25 |  | 0 | 2024-10-28 | 11
Incidental not speaking characters | 2 |  | 10 | 2024-10-14 | 2024-10-25 |  | 0 | 2024-10-28 | 11
Modeling & Texturing |  |  | 261.5 | 2024-10-28 | 2025-11-13 |  | 0 | 2025-10-28 | 381
Episodic content | 8 | 12 | 60 | 2025-02-26 | 2025-05-23 |  | 0 | 2025-05-21 | 86
Comparse umane (2 adulti+bambino) | 3 |  | 36 | 2025-03-14 | 2025-05-07 | 7 | 0 | 2025-05-05 | 54
Comparse umane (2 adulti+bambino) | 5 |  | 60 | 2025-02-26 | 2025-05-23 | 8 | 0 | 2025-05-21 | 86
Episodic content | 30 | 0.5 | 13.5 | 2025-05-08 | 2025-05-27 |  | 0 | 2025-05-27 | 19
Episodic character (cambio colore vestito o cappelli) | 27 |  | 13.5 | 2025-05-08 | 2025-05-27 | 21 | 0 | 2025-05-27 | 19
Episodic character (cambio colore vestito o cappelli) | 3 |  | 1.5 | 2025-05-26 | 2025-05-27 | 22 | 0 | 2025-05-27 | 1
Episodic content | 8 | 12 | 48 | 2025-05-27 | 2025-08-04 |  | 0 | 2025-08-01 | 69
Episodic speaking human characters | 4 |  | 48 | 2025-05-27 | 2025-08-04 | 24 | 0 | 2025-08-01 | 69
Episodic speaking human characters | 4 |  | 48 | 2025-05-27 | 2025-08-04 | 25 | 0 | 2025-08-01 | 69
Episodic content | 12 | 12 | 72 | 2025-08-04 | 2025-11-13 |  | 0 | 2025-11-12 | 101
Episodic incidental characters | 6 |  | 72 | 2025-08-04 | 2025-11-13 | 27 | 0 | 2025-11-12 | 101
Episodic incidental characters | 6 |  | 72 | 2025-08-04 | 2025-11-13 | 28 | 0 | 2025-11-12 | 101
Episodic content | 358 | 1.5 | 184 | 2024-10-28 | 2025-07-25 |  | 0 | 2025-07-11 | 270
Episodic Props | 119 |  | 179 | 2024-11-05 | 2025-07-25 | 15 | 0 | 2025-07-14 | 262
Episodic Props | 119 |  | 179 | 2024-11-05 | 2025-07-25 | 16 | 0 | 2025-07-14 | 262
Episodic Props | 119 |  | 179 | 2024-10-28 | 2025-07-18 | 17 | 0 | 2025-07-04 | 263
Episodic content | 58 | 0.5 | 29 | 2025-07-02 | 2025-08-11 |  | 0 | 2025-08-12 | 40
Episodic Prop (solo TX) |  |  | 29 | 2025-07-02 | 2025-08-11 | 100 | 0 | 2025-08-12 | 40
Episodic content | 10 | 20 | 204 | 2024-10-28 | 2025-08-25 |  | 0 | 2025-08-08 | 301
Episodic environment | 1 |  | 20 | 2025-07-28 | 2025-08-25 | 33 | 0 | 2025-08-25 | 28
Episodic environment | 1 |  | 20 | 2025-07-28 | 2025-08-25 | 34 | 0 | 2025-08-25 | 28
Episodic environment | 1 |  | 20 | 2025-07-21 | 2025-08-18 | 35 | 0 | 2025-08-18 | 28
Episodic environment | 7 |  | 140 | 2024-10-28 | 2025-05-23 | 18 | 0 | 2025-05-12 | 207
Episodic content | 2 | 5 | 69 | 2025-05-26 | 2025-09-01 |  | 0 | 2025-08-29 | 98
Night version - EXT Macro environment | 1 |  | 5 | 2025-08-26 | 2025-09-01 | 40 | 0 | 2025-09-02 | 6
Night version - EXT Macro environment | 1 |  | 5 | 2025-05-26 | 2025-05-30 | 42 | 0 | 2025-06-02 | 4
Episodic content | 2 | 10 | 69 | 2025-06-03 | 2025-09-08 |  | 0 | 2025-09-08 | 97
Seasonal version - EXT Macro environment | 1 |  | 10 | 2025-08-26 | 2025-09-08 | 39 | 0 | 2025-09-09 | 13
Seasonal version - EXT Macro environment | 1 |  | 10 | 2025-06-03 | 2025-06-16 | 45 | 0 | 2025-06-17 | 13
Formulas:
WD = WORKDAY([start],D3)

## Settings
Settings | [10 empty] | Gantt
Project Details |  |  | Project Role Details |  |  |  | Project Role Details
| Project Title: | Progetto1 |  | Role | Code | # |  | Name | Role | Code
|  |  |  | Project Managment | PM | 1 |  | Luigi | Project Managment | PM
| Project Manager: | gg |  | Coding | COD | 0 |  | Simona | Design | DES
|  |  |  | Design | DES | 2 |  | Matteo | Design | DES
| Project Priority: | High |  | Animator | ANIM | 0

## Gantt
Gantt | [20 empty] | Projec Timespan: | [6 empty] | 2024-07-02 | [6 empty] | 2024-05-10 | [6 empty] | 2024-05-10 | [26 empty] | Projec Manager: | [6 empty] | gg | [10 empty] | Settings
=MIN(ITEMS_START)
[10 empty] | =NETWORKDAYS(plan_start;MAX(ITEMS_END)) | [5 empty] | =IF(i.id<>"";IF(d.id<id;"au";IF(i.id>id;"ad";""));"") | [6 empty] | =IFERROR("("& d_type &")" & d_name;"")
IF(LEN(d_name)>7;LEFT(d_name;7)&"...";d_name
Unicode Icons
⚠ | ♦ | ⟼ | ⥽ | ↗ | ↘ |  |  | Actual plan | [9 empty] | Base plan | time axis 2024-06-25 to 2024-10-02
|  |  |  | ↖ | ↙ |  |  | update on: | [9 empty] | Saved on:
ids |  |  | Item Details |  |  |  |  | x-xxx-xx | [9 empty] | x-xxx-xx
id | s id | r id | Type | Description | Role | Team | ⚠ | ind. Start | ind. End | d. Id | d. Item |  | d. Conn | d. Lag | Work days | Start | End | Start | End | % | m | m | g | v | l | m | m | g | v | l | m | m | g | v | l | m | m | g | v | l | m | m | g | v | l | m | m | g | v | l | m | m | g | v | l | m | m | g | v | l | m | m | g | v | l | m | m | g | v | l | m | m | g | v | l | m | m | g | v | l | m | m | g | v | l | m | m | g | v | l | m | m
1 |  |  | S | planning |  |  | ⚠ | 2024-07-02 | 2024-07-26 | [5 empty] | 9 | Start: 2024-07-02; End: 2024-07-12
2 |  |  | T | task p1 | DES | Simona |  | 2024-07-02 | 2024-07-12 | 3 | ↙ | (T) task p2 |  |  | 9 | Start: 2024-07-02; End: 2024-07-12
3 |  |  | T | task p2 | DES | Matteo |  |  |  | 2 | ↖ | (T) task p1 |  |  | 3
4 |  |  | T | task p3 | PM | Luigi |  |  |  | 3 | ↖ | (T) task p2 |  |  |  | x-xxx-xx Start: 1900-01-16
5 |  |  | M | milestone 1 | PM | Luigi |  |  |  | 4 | ↖ | (T) task p3
6 |  |  | S | implementetion | [5 empty] | 5 | ↖ | (M) milestone ...
7 |  |  | T | task i1 | PM | Luigi |  |  |  | 6 | ↖ | (S) implemente...
8 |  |  | T | task i2 | DES | Simona |  |  |  | 7 | ↖ | (T) task i1
9 |  |  | T | task i3 | DES | Matteo |  |  |  | 8 | ↖ | (T) task i2
10 |  |  | M | milestone 2 | PM | Luigi |  |  |  | 9 | ↖ | (T) task i3
11 |  |  | T | milestone 2 | DES | Simona |  |  |  | 10 | ↖ | (M) milestone ...
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36